Conditions of Contract  
  
Quotation - Works

Effective Date: 1 July 2014  
Version No. 5.0

This page is left intentionally blank

**Table of Contents**

1 Interpretation of Terms 5

2 Formation of Contract 7

3 Nature of Contract 7

3.1 Basis of Payment 7

3.2 Applicable Law 8

4 Entire Agreement 8

5 General Obligations of the Parties 8

6 Principal’s Responsibilities and Obligations 8

7 Superintendent and Superintendent's Representative 8

8 Directions 8

9 Contractor's Responsibilities and Obligations 9

10 Contractor's Representative 9

11 Power to Dismiss Workers 9

12 Status of Contractor 9

13 Notices 10

13.1 Services of Notices 10

13.2 Effective on Receipt 10

14 Site Rules 10

15 Confidentiality, Publicity and Media 10

15.1 Confidentiality 10

15.2 Media and Publicity 11

16 Industry Accreditation and Standards 11

17 Local Development 11

18 Indigenous Development Plan 12

19 Project Control Plan 12

20 Insurances 12

20.1 Workers Compensation Insurance 12

20.2 Public Liability Insurance 13

20.3 Lodgement of Certificates of Currency 13

21 Time for Commencement 13

22 Time for Completion 13

23 Invoicing and Payments 13

24 Storage of Contractor's Material 14

25 Working Hours 14

26 Obvious Work 15

27 Access to Works and Material 15

28 Materials and Workmanship 15

29 Proprietary Items 15

30 Connection of Services 15

31 Work Health and Safety Management 15

31.1 Definitions 15

31.2 WHS Management Plan 16

31.3 Appointment of Contractor as Principal Contractor 16

31.4 General Obligations 17

31.5 High Risk Construction Work 17

31.6 Contractor’s Obligations to Inform 17

31.7 Right of Principal to Monitor and Audit 17

31.8 Powers of Superintendent Regarding Work Health and Safety 18

31.9 Works Involving Asbestos 18

31.10 Design, Manufacture and Installation Safety Matters 18

31.11 Breach by Contractor 19

31.12 Work in the vicinity of Power and Water Assets 19

31.13 Work in the vicinity of Natural Gas Pipelines 19

31.14 Fire Precautions 19

31.15 Scaffolding and Excavation 19

31.16 Disabled Access 20

32 Precautions in Carrying Out Works 20

33 Damage to Services 20

34 Care of Work and Cleaning Up 20

35 Protection and Provision for Traffic 21

36 Protection for Occupants 21

37 Protection of Property 21

38 Protection of Equipment 21

39 Strong Wind Precautions 21

40 Custody of Keys – Power and Water Assets 21

41 Variations 21

42 Defects Liability Period 21

43 Assignment 22

44 Sub-Contracting 22

45 Disputes 22

46 Termination 23

47 Rights of Principal to Recover Monies 23

48 Contractor's Performance Report 23

49 Goods and Services Tax 24

50 Privacy 24

# Conditions of Contract

# Interpretation of Terms

In these Conditions of Contract, unless the context otherwise requires:

**'Agency'** means a department, agency or statutory authority of the Northern Territory of Australia.

‘**Annexure’** means the section in the RFQ detailing the specific requirements applicable to the Conditions of Quoting and Contract.

**'Completion'** means the Superintendent has determined that the execution of the Works has reached the stage where the Works are complete except for minor omissions and/or minor defects.

**'Contract'** means the document which constitutes or evidences or, as the case may be, all the documents which constitute or evidence the final and concluded agreement between the Principal and the Contractor concerning the execution of the Works.

**'Contractor'** means the legal entity that, as party to the Contract, is bound to execute the Works in accordance with the Contract and includes the successors and lawful assigns of the Contractor.

**'Contractor’s Quotation'** means the Quotation submitted by the Contractor in response to the RFQ.

**'Date of Acceptance'** means the date appearing on the Notice of Acceptance and if no date appears is the date on which the Principal sent the Notice of Acceptance to the Contractor.

**'Defects Liability Period'** means the defects liability period referred to in the clause entitled ‘Defects Liability Period’ and stated in the Annexure.

**'Documents'** means all material stored by any means and produced or used by the Contractor or sub-contractor in the course of the Contract including sketches, plans, drawings, specifications, designs, estimates, calculations, reports, models, and other articles, equipment, information, files and data.

**'Drawings’** means the drawings referred to in the Scope of Works and any modification of such drawings notified to the Contractor by the Superintendent and includes such other drawings as may from time to time be supplied to the Contractor by the Superintendent, or the use of which has been permitted by the Superintendent, for the purposes of the Contract.

**'Indigenous Person’** is a person of Australian Aboriginal or Torres Strait Islander descent who identifies themselves as Indigenous and is accepted in the community in which they live as an Indigenous person.

**'Lump Sum'** means the total sum which will have become payable to the Contractor by the Principal upon completion of the Works.

**'Notice of Acceptance'** means the written notification and any accompanying documentation sent to the Contractor by the Principal advising acceptance of its Quotation to execute the Works.

**'Order'** means an order issued on the Contractor by the Superintendent, whether on paper or by electronic means, which conveys the essential details of a particular work requirement under the Contract and includes any methods of ordering the Works specifically referred to in the Contract.

**'Principal'** means the Northern Territory of Australia. The Principal for Power and Water contracts is the Power and Water Corporation.

**'Portion of the Works'** means the Superintendent has directed the Contractor to carry out particular work in accordance with the Contract, such work representing a part of the total Works required under the Contract.

**'Rate'** means the rate per any section or item of the Works as stated in the Contract.

**'Request for Quotation (RFQ)'** means the document(s) containing the Conditions of Quoting and Contract, the Annexure, Special Conditions of Contract (if any), Scope of Works, Response Schedules, Drawings and any other document issued for the purposes of inviting Quotations for the Works.

**'Schedule of Rates'** means any schedule included in the Contract which, in respect of any section or item of work, shows the respective unit rate of payment for execution of that work and which may also include lump sums, provisional sums, other sums, quantities and prices.

**'Site’** means the lands and other places to be made available and any other lands and places made available to the Contractor by the Principal for the purpose of the Contract.

**'Scope of Works'** means the sections of the RFQ detailing the technical requirements of the work to be carried out as existing at the Date of Acceptance of the Quotation and any modification of such Works thereafter directed or the use of which has been permitted by the Superintendent for the purposes of the Contract.

**'sub-contractor'** means a person other than the Contractor’s employees, engaged by the Contractor who provides goods, services or Works to the Contractor.

**‘Superintendent’** means the person named in the Annexure as the Superintendent or other person from time to time appointed in writing by the Principal to be the Superintendent for the purposes of the Contract, and notified as such in writing to the Contractor by the Principal.

**‘Tax Invoice’** has the meaning given in *A New Tax System (Goods and Services Tax) Act 1999*.

**'Works'** means the whole of the work to be executed in accordance with the Contract, including all variations and remedial work provided for by the Contract.

In the Contract, unless the contrary intention appears:

1. headings are for the purpose of convenient reference only and shall not be used in the interpretation of these conditions;
2. the singular includes the plural and vice-versa;
3. a reference to one gender includes the other;
4. a reference to a person includes a body politic, body corporate or a partnership joint venture, incorporated association, government, local government authority or agency;
5. a reference to a party includes that party’s administrators, successors, and permitted assigns, including any person to whom that party novates any part of the Contract;
6. if the last day of any period prescribed for the doing of an action falls on a day which is not a Working Day, the action shall be done no later than the end of the next Working Day;
7. a reference to time is to Australian Central Standard Time;
8. a reference to an Act is a reference to an Act of the Commonwealth, State or Territory of Australia, as amended from time to time, and includes a reference to any subordinate legislation made under the Act;
9. a reference to a ‘dollar’, ’$’, ’$A’ or ’AUD’ means the Australian dollar unless otherwise stated;
10. a reference to a “measurement” means Australian legal units of measurement unless otherwise specified;
11. a reference to a specification, publication, Commonwealth policy or other document is a reference to that specification, publication, Commonwealth policy or document, in effect on the Effective Date and updated from time to time, or alternatively, a reference to another version of the document if agreed in writing between the parties;
12. the word ‘includes’ in any form is not a word of limitation;
13. a reference to a clause includes a reference to a subclause of that clause; and
14. a reference to a clause, paragraph, schedule or annexure is to a clause or paragraph of, or schedule or annexure to, this Contract, and a reference to this Contract includes any schedule or annexure.

# Formation of Contract

The Contract is comprised of:

1. these Conditions of Contract and any Special Conditions;
2. the Notice of Acceptance;
3. the RFQ;
4. the Contractor’s Quotation response; and
5. any other document expressly referred to in items (a) to (c) of this clause as forming part of the contract (together the Contract).

If there is any inconsistency between any part of the Contract, a descending order of precedence shall be accorded to the:

1. Special Conditions (if any);
2. these Conditions of Contract;
3. Annexure to the Conditions of Quoting and Contract;
4. Notice of Acceptance;
5. General clauses;
6. Scope of Work;
7. Drawings and Scope of Work included in the RFQ;
8. any other document expressly referred to in items (a) to (g) inclusive of this clause as forming part of the Contract;
9. Conditions of Quoting and all other documents, other than those specified above in (a) to (g) inclusive, forming the RFQ or the Contract (other than the Contractor’s Quotation); and
10. the Contractor’s Quotation response including any Drawings;

so that the provision in the higher ranked document, to the extent of the inconsistency, shall prevail.

# Nature of Contract

## Basis of Payment

The Contractor shall be paid either on a Lump Sum or a Schedule of Rates basis as stated in the Annexure.

Where payment is to be made on a Lump Sum basis the sum payable shall, subject to any adjustment made pursuant to the Contract, be the Lump Sum.

Where payment is to be made on a Schedule of Rates basis the quantities in the Schedule are estimated quantities only and are not to be taken as actual or correct quantities of work to be carried out: the lower and upper limits of accuracy for each quantity are eighty five per cent (85%) and one hundred and fifteen per cent (115%) respectively of the stated quantity. When the actual quantity is greater than the upper limit or less than the lower limit, an adjustment may be made to the rate applicable to the quantity outside the limits of accuracy. Any adjustment to the rate shall be as agreed between the Contractor and the Superintendent, or in the event of failure to agree, as determined by the Superintendent.

The Contract shall be on a firm price basis.

## Applicable Law

The Contract shall be governed by and construed in accordance with the laws of the Northern Territory of Australia.

# Entire Agreement

The Contract formed between the parties to undertake the Works constitutes the entire agreement between the parties and supersedes any previous agreements or understandings.

# General Obligations of the Parties

Both the Principal and the Contractor will, at all times:

1. act reasonably in performing their obligations and exercising their rights under the Contract;
2. diligently perform their respective obligations under this Contract; and
3. work together in a collaborative manner.

# Principal’s Responsibilities and Obligations

The Principal shall give or cause to be given to the Contractor timely instructions, decisions and information sufficient to define the requirements of the Works.

Unless the Contract expressly provides otherwise, the Principal shall give any direction to the Contractor in accordance with the clause titled “Directions” and “Notices”.

# Superintendent and Superintendent's Representative

The Superintendent for the purposes of the Contract is as defined in the Annexure.

For the purpose of exercising some of the powers, duties, discretions and authorities, vested in him on behalf of the Principal, the Superintendent may from time to time appoint a representative (‘**Superintendent’s Representative**’). The limitations imposed on the Superintendent's Representative will be as laid down in the notice of appointment.

The Contractor shall recognise and accept notices from the Superintendent's Representative as if the Superintendent issued such. Any reference to the Superintendent within these conditions shall be deemed to be a reference to the Superintendent's Representative so far as it concerns the exercise of the Superintendent's Representative's powers by virtue of his appointment.

# Directions

The Superintendent has the power to issue directions under the Contract and the Contractor shall comply with any direction either orally or in writing issued, given or served upon him by the Superintendent. Any direction given orally shall, as soon as practicable after it is given, be confirmed in writing. For the purposes of this clause the work "direction" includes any agreement, approval, authorisation, certificate, decision, demand, determination, direction, explanation, instruction, notice, notification, order, permission, rejection, request or requirement which the Superintendent may make, give or issue pursuant to the provisions of the Contract.

Where such phrases as "as may be directed", "approval", or "approved" or the like are used in the Contract they shall mean that the direction and approval of the Superintendent is referred to, irrespective of any trade usage.

# Contractor's Responsibilities and Obligations

The Contractor shall be responsible for executing the Works in accordance with these conditions, the Drawings and Scope of Works.

The Contractor shall be liable for any loss or damage to the Works from any cause whatsoever (except loss or damage caused by any negligent act, omission or default of the Principal or employees or agents of the Principal), and shall at his own cost make good any such loss or damage.

The Contractor shall, unless the Contract otherwise provides, supply at his own cost and expense everything necessary for the proper completion of the Works and the proper performance of his obligations under the Contract.

The Contractor shall comply with all provisions of all Acts of the Commonwealth of Australia, Acts of the Northern Territory, and with the requirements of all regulations, by-laws, orders or subordinate legislation made or issued under any such Act,, the Northern Territory Procurement Code, and all requirements of any relevant authority, regulator or standard setting entity as shall be in force in the place affecting or applicable to the Works or the execution of the Works.

# Contractor's Representative

The Contractor shall personally supervise the execution of the Works or have a competent representative (‘**Contractor’s Representative**’) acceptable to the Superintendent present on the Site at all times where the work is being carried out.

The Contractor or his representative shall be equipped with a mobile telephone or employ a suitable communications system acceptable to the Superintendent.

The Contractor shall notify the Superintendent in writing of the name of his representative and prior to any subsequent change of his representative shall obtain the approval of the Superintendent.

Any direction given to the Contractor's representative shall be deemed to be a direction issued to or served upon the Contractor.

Matters within the knowledge of the Contractor's representative shall be deemed to be within the knowledge of the Contractor.

The Contractor or his representative shall have sufficient command of the English language and of Australian building and technical terminology to be able to read, converse and receive instructions in English.

# Power to Dismiss Workers

The Superintendent may require the instant dismissal from the Works, of any agent, overseer, foreman or other person employed on the Works, or in connection with the Works, whether employed by the Contractor or not and the Contractor shall immediately comply with or ensure immediate compliance with such requirement and the Contractor shall not again employ a person so dismissed on or in connection with the Works.

# Status of Contractor

The Contractor, its employees and sub-contractors thereof, in performing the Works, are not for any purpose a servant or employee of the Principal.

# Notices

## Services of Notices

Notice must be:

1. in writing, in English and signed by a person duly authorised by the sender; and
2. hand delivered or sent by prepaid post or by electronic means to the recipient's address for Notices set out in the Contract, as varied by any Notice given by the recipient to the sender.

## Effective on Receipt

Any notice given in accordance with sub clause 13.1 sent to the address set out in the Contract, takes effect when it is taken to be received (or at a later time specified in it) and is taken to be received:

1. if hand delivered, on delivery;
2. if sent by post, three (3) Working Days after the date of posting; and
3. if sent by electronic transmission, on receipt by the sender of a transmission report from the despatching machine indicating that the notice sent was received in its entirety at the recipient’s machine unless, within eight (8) Working Hours after the transmission, the recipient informs the sender that it has not received the entire Notice;

but if the delivery, receipt or transmission is not on a Working Day or is after 4.30pm on a Working Day, the Notice is taken to be received at 8.00am on the next Working Day.

# Site Rules

The Contractor, his employees and sub-contractors required to enter the Site in connection with the Works shall comply with all rules and regulations in force at the Site, including security screening through Criminal History Checks where required. Also refer to the specific Site Rules nominated in the General Clauses section of the RFQ.

The Contractor is responsible for obtaining all relevant permits and the payment of all associated fees and/or charges which are levied by the appropriate Authority.

# Confidentiality, Publicity and Media

## Confidentiality

1. For the purposes of this clause 15.1 “Confidential Information” means any information or material relating to the Contract or the Works including (without limitation):
2. any information that by its nature is confidential;
3. any information designated as confidential; and
4. any information that the Contractor knows is confidential.
5. The Contractor shall hold all Confidential Information in confidence and shall not make any use of it, except for the purposes of performing its obligations or exercising its rights under the Contract and shall not disclose or permit or cause the Confidential Information to be disclosed to any person, except:
6. as authorised by the Principal under the Contract or otherwise;
7. to its employees or contractors, to the extent needed to perform their obligations under the Contract;
8. where the disclosure is required to be disclosed by law.
9. The Contractor shall ensure that its employees and all consultants, contractors and suppliers engaged by the Contractor for the performance of the Contract comply with the requirements of this clause 15.1.

## Media and Publicity

1. The Contractor shall not issue or be involved with the release of, any information, publication, statement, interview, advertisement (other than the legitimate advertising for sub-contractors), award nomination, document or article for publication concerning the Contract, the Works or the site in any media without the prior written approval of the Principal.
2. Prior to taking any action or doing anything the Contractor shall refer:
3. any media enquiries concerning the Contract, the site, the Principal or the Works to the Principal for the Principal’s written response; and
4. any media requests concerning the Contract, the site, the Principal or the Works (including, without limitation, requests to access or take photographic or video footage of the site) to the Principal, for the Principal’s written consent, which consent may be given or withheld, in the Principal’s absolute discretion.
5. The Contractor shall ensure that its employees and all consultants, contractors and suppliers engaged by the Contractor for the performance of the Contract comply with the requirements of this clause 15.2 and obtain the Principal’s prior written consent (through the Contractor) before responding to enquiries or publishing anything of the type referred to in this clause 15.2.

# Industry Accreditation and Standards

Where applicable, the Contractor shall:

1. maintain the currency of accreditation with Contractor Accreditation Limited during the life of the Contract; and
2. comply with all industry standards on:
3. training;
4. engagement, supervision and payment of sub-contractors;
5. compliance measures;
6. penalties; and
7. termination arrangements.

# Local Development

The Contractor shall, except in those cases where the Contractor can demonstrate to the Principal that it is impractical for commercial, technical or other reasons to do so use on, or in connection with, the Works:

1. labour, including Indigenous labour, available within the Northern Territory;
2. services located and obtain supplies/materials available within the Northern Territory; and
3. accredited apprentices/trainees who are registered in the Northern Territory.
4. In complying with the use of accredited apprentices/trainees, the Contractor may:

* directly employ apprentices/trainees;
* utilise group training scheme apprentices/trainees;
* utilise sub-contractors apprentices/trainees;
* utilise any combination of the above.

The Contractor is solely responsible for ensuring that the specified requirements are met.

The Contractor shall, when requested by the Principal, submit a written report concerning the compliance with the provisions of this clause. The Principal may conduct spot audits on compliance with the use of accredited apprentices/trainees on the Works.

The Contractor’s level of compliance with this requirement will be included in the Performance Report on the Contractor at the completion of the Contract and will be taken into consideration for further Northern Territory Government contracts for a period of twelve (12) months.

# Indigenous Development Plan

Where an Indigenous Development Plan has been specified, the Contractor will maintain and implement the Indigenous Development Plan throughout the course of the Contract.

Within fourteen (14) days of the Date of Acceptance, the Contractor shall submit to the Superintendent for approval one copy of the Indigenous Development Plan. The Superintendent shall within a reasonable time from receipt either approve the Indigenous Development Plan, or reject it, giving reasons for the rejections. The Contractor shall rectify the deficiencies and resubmit the Indigenous Development Plan for approval.

The Contractor shall provide timesheets with employment (hours worked) and training records for all Indigenous people engaged on the works with all Progress claims for Payment.

The Contractor will be required to provide the Principal with a report on compliance (achievements against the objectives/goals) with the Indigenous Development Plan within thirty (30) days of the completion of the Contract.

# Project Control Plan

Where a Project Control Plan has been specified, the Contractor will maintain and implement the Project Control Plan throughout the course of the Contract. The Superintendent will provide a framework document with guide notes to assist in the preparation of the document, which should be prepared by the Contractor and not a third party.

Within fourteen (14) days of the Date of Acceptance, the Contractor shall submit to the Superintendent for approval one copy of the Project Control Plan. The Superintendent shall within a reasonable time from receipt either approve the Project Control Plan, or reject it, giving reasons for the rejections. The Contractor shall rectify the deficiencies and resubmit the Project Control Plan for approval.

# Insurances

## Workers Compensation Insurance

For the purpose of this clause “worker” shall have the definition it is given in the *Workers Rehabilitation and Compensation Act 2009*.

Before commencing work under the Contract, the Contractor shall take out and maintain for the duration of the Contract appropriate Workers Compensation insurance cover for all workers employed by the Contractor. This cover shall comply with the *Workers Rehabilitation and Compensation Act 2009* of the Northern Territory and policies shall be purchased from Northern Territory approved insurers. Details can be found at the web address:  
www.worksafe.nt.gov.au/ServiceProviders/Insurers/Pages/Find-an-Approved-Insurance-Company.aspx

The Contractor shall ensure that all sub-contractors who employ workers have Workers Compensation insurance cover in accordance with the *Workers Rehabilitation and Compensation Act 2009*.

The Contractor shall ensure that all persons employed under labour hire agreements, whether by the Contractor or through a Labour Hire Firm, are appropriately covered by Workers Compensation insurance.

Self-employed Contractors must ensure that they have adequate insurance coverage in place.

The Contractor shall be responsible for ensuring that all sub-contractors have appropriate insurance policies in place.

## Public Liability Insurance

Before commencing work under the Contract, the Contractor shall take out, and shall maintain during the currency of the Contract, a Public Liability policy of insurance to cover its liabilities to third parties.

The Policy shall be for an amount of not less than the sum stated in the Annexure, for any one occurrence.

The effecting of insurance shall not limit the liabilities or obligations of the Contractor under other provisions of the Contract.

The Contractor shall ensure that all sub-contractors take out Public Liability Insurance that meets the requirements of this clause.

## Lodgement of Certificates of Currency

The Contractor shall provide the Principal with copies of Certificates of Currency and summaries of key provisions for all insurance policies required under clause 20 including those of any sub-contractors (including self-employed contractors and persons employed under labour hire agreements):

1. prior to commencing the Works under the Contract;
2. within two (2) days of a written request by the Principal;
3. within seven (7) days after the Contractor renews an Insurance Policy; and
4. within seven (7) days after the Contractor makes any change to an Insurance Policy.

The Contractor will not cancel any Insurance Policy, or conduct itself in a manner that brings about such a cancellation of an Insurance Policy, except with the written consent of the Principal.

# Time for Commencement

The Contractor shall commence the Works within the time stated in the Annexure and shall, unless otherwise specified, give at least four (4) days written notice to the Superintendent prior to the commencement of work.

# Time for Completion

The Contractor shall complete the Works within the time stated in the Annexure or within such extended time as agreed to in writing by the Superintendent.

# Invoicing and Payments

The Contractor shall submit to the Superintendent a Tax Invoice at intervals of not less than one (1) month or as otherwise determined by the Superintendent, showing the value of the work carried out in performance of the Contract.

The Contractor's Tax Invoice shall include details of any Adjustments under clause titled Goods and Services Tax of the Conditions of Contract and an explanation as to how such Adjustments were calculated.

The Contractor shall provide any further details in regards to the Works and/or any Tax Invoice upon request by the Superintendent.

Principal shall make payments within thirty (30) days of receipt of a Tax Invoice that is not disputed.

Failure by the Principal to pay the amount by the due date:

1. will not be grounds to vitiate or avoid the contract; and
2. will entitle the Contractor to make a claim for interest penalties on the late payment.

Interest penalties must be claimed within ninety (90) days of the date the late payment was made by the Principal and the claim must be in the form of a Tax Invoice. Interest penalties are to be calculated daily, for the period after the due date until the date payment is made by the Principal, at the ninety (90) day bank bill swap rate published on 1 June each year by the Australian Financial Markets Association. Where interest penalty period spans 1 June in any year, the rate shall be the rate published in the year the original invoice was issued.

The Principal will not be liable for interest penalties on any payments in respect of interest penalties.

# Storage of Contractor's Material

The Contractor's materials and plant shall only be stored in the location approved by the Superintendent.

If no storage facilities are available, it shall be the responsibility of the Contractor to provide storage facilities.

All care shall be taken to avoid inconvenience to persons occupying and visiting the site of the Works.

# Working Hours

The customary working hours and ordinary working days shall be those for day workers as stated in the Building and Construction Industry (NT) Award (or Electrical Engineering and Contracting Industries (NT) Award for Power and Water) or other relevant awards and no work will be performed outside of customary working hours or on other than ordinary working days without the prior approval of the Superintendent.

The working hours and working days of the Principal's supervisory personnel shall be 8.00 am to 4.30 pm Monday to Friday excluding a day that is a public holiday in the Northern Territory (‘**Working Day**’). The Contractor shall provide at least forty-eight (48) hours written prior notice to the Superintendent of the intention to work outside the working hours and working days of the Principal's supervisory personnel.

Notwithstanding the preceding paragraphs, the Contractor may carry out work outside the customary working hours or ordinary working days without the prior approval of the Superintendent, where it is necessary in the interests of safety of the Works or where the work is required to protect life or property. In such circumstances the Contractor shall inform the Superintendent in writing of the circumstances as early as possible.

# Obvious Work

The Contractor shall carry out all work, which obviously forms part of the Contract even though not specifically listed or detailed in the Scope of Works or Drawings.

# Access to Works and Material

The Superintendent or any other persons authorised by him, shall have free and uninterrupted access at all times to the Works and during working hours to any workshop or premises not on the site of Works where materials may be in preparation or stored for the purpose of the Contract.

The Contractor if so required by the Superintendent shall give the Superintendent all particulars as to the mode and place of manufacture of any of the materials proposed to be used in connection with the Contract and shall facilitate inspection of the materials.

# Materials and Workmanship

All material used in the Works and the standards of workmanship shall conform to the provisions of the Contract. In the absence of such provisions that material or standard of workmanship shall be of a kind that is fit for its purpose and is consistent with the nature and character of the Works.

Any material not otherwise specified shall be new and, where applicable material and workmanship shall be in accordance with the relevant standard of Standards Australia. If the Superintendent is of the opinion that any material or the work, whether fixed or not, is unsatisfactory he may direct its replacement, removal or correction at the Contractor's expense.

# Proprietary Items

Where items are specified as being a particular maker's brand, trade name or catalogue number, then unless specifically stated to the contrary, it is not intended to give any preference to the manufacturer or brand mentioned wherever a proprietary item is specified.

If the Contractor proposes to use a substitute proprietary item, he must provide full particulars of the item he proposes to use to the Superintendent for approval and the Superintendent shall decide whether or not the proposed substitute may be used.

# Connection of Services

Unless otherwise specified the Contractor is responsible for connection of all water, drainage, sewerage, gas and electricity services to the Works and shall apply for all relevant permits and pay all associated fees and/or charges which are levied by the appropriate Authority.

# Work Health and Safety Management

## Definitions

For the purposes of this clause 31

**'Construction Project'** means any work carried out in connection with the construction, alteration, conversion, fitting‑out, commissioning, renovation, repair, maintenance, refurbishment, demolition, decommissioning or dismantling of a structure where the cost of the work is $250 000 or more;

**'High Risk Construction Work'** has the meaning given to it in the *WHS Act*;

**'Plant'** means any machinery, equipment, appliance, container, implement, tool or any component thereof and anything connected or fitted thereto;

**'Principal Contracto**r**'** means a person authorised to have management and control of the Site for the purposes of the Works and who is appointed by the Principal under clause 31.3 as a principal contractor for the purposes of the *WHS Act*;

**'Safe Work Method Statement'** has the meaning given to it in the *WHS Act;*

**'Structure'** has the meaning given to it in the *WHS Act*;

**'Substance'** means any natural or artificial substance, whether solid, liquid, gas or vapour;

**'*WHS Act*'**means the *Work Health and Safety (National Uniform Legislation) Act 2011 (NT)* and includes subordinate legislation made under that Act including regulations and approved codes of practice as well as any amendment, re-enactment or replacement of such Act ; and

**'WHS Management Plan'** means a health and safety management plan or system in respect of workplace health and safety matters in connection with the Works.

## WHS Management Plan

1. This clause 31.2 only applies where the Works comprise a Construction Project.
2. Prior to commencing any Works at the Site the Contractor must prepare a WHS Management Plan and provide it to the Principal.
3. The Contractor must:
4. for the duration of the Contract, provide:

* the Principal; and
* each person who is to carry out construction work in connection with the Works,
* any further information in relation to the WHS Management Plan that may be requested of the Contractor, including allowing those parties to inspect the WHS Management Plan at their request;

1. maintain the WHS Management Plan throughout the course of the Contract;
2. carry out the Works in accordance with the WHS Management Plan;
3. review and, as necessary, revise the WHS Management Plan and provide any such revised plan to the Principal and to each person who is to carry out work in connection with the Works (including sub-contractors); and
4. keep a copy of the WHS Management Plan until the Works to which it relates have reached completion, or for at least two years after a notifiable incident occurs in connection with the Works, whichever is the latter.
5. The WHS Management Plan must address all those matters required to be covered in a WHS Management Plan as specified in the *WHS Act*.
6. The Contractor will not be relieved from compliance with any of its obligations under the Contract or from any of its liabilities whether under the Contract or otherwise according to law as a result of:
7. any direction by the Superintendent concerning the WHS Management Plan or the Contractor's compliance or non-compliance with the WHS Management Plan;
8. any audit or other monitoring by the Principal or its nominee of the Contractor's compliance with the WHS Management Plan; or
9. any failure by the Superintendent, or anyone else acting on behalf of the Principal, to detect any defect in or omission from the WHS Management Plan including where any such failure arises from any negligence on the part of the Superintendent or other person.

## Appointment of Contractor as Principal Contractor

1. This clause 31.3 only applies where the Works comprise a Construction Project.
2. On and from the Date of Acceptance, the Principal appoints and the Contractor accepts such appointment as the Principal Contractor for the Works for the purposes of the *WHS Act* and the Contractor must:
3. discharge the duties imposed on a Principal Contractor by the *WHS Act* in respect of carrying out the Works;
4. accept that, as Principal Contractor, the Contractor is the person responsible for the control and management of the Site and the Works at all times until Completion;
5. ensure that any sub-contract entered into contains enforceable obligations requiring the sub-contractor to comply with the *WHS Act* and cooperate and comply with any direction of the Contractor in relation to work health and safety matters.

## General Obligations

The Contractor must:

1. carry out a risk assessment in relation to all of the Works;
2. carry out the Works safely and manage the risk of harm to persons or property;
3. ensure that it complies with any statutory requirement that requires a person to be authorised, licensed, supervised or to have prescribed qualifications or experience or that requires a workplace, Plant, Substance or design, or work (or class of work) to be authorised or licensed;
4. put in place and maintain suitable emergency management procedures relevant to the Works; and
5. if requested by the Superintendent, produce evidence of any approvals including any authorisations, licences, prescribed qualifications or experience, or any other information relevant to work health and safety (as the case may be) to the satisfaction of the Superintendent before the Contractor or any sub-contractor commences any Works; and
6. generally comply with the requirements of the *WHS Act*.

## High Risk Construction Work

Where the Works include or comprise High Risk Construction Work, the Contractor will ensure that:

1. any person carrying out high risk construction work is licensed in accordance with the *WHS Act*;
2. before the work is carried out, a Safe Work Method Statement is prepared in respect to the High Risk Construction Work in accordance with the *WHS Act*, and that a copy of the Safe Work Method Statement is:
3. provided to the Superintendent before the High Risk Construction Work is carried out and at any other time requested by the Superintendent; and
4. kept at the area of the Site where the High Risk Construction Work is being or is to be carried out;
5. the High Risk Construction Work is carried out in accordance with the Safe Work Method Statement.

## Contractor’s Obligations to Inform

The Contractor must keep the Superintendent fully informed of all health and safety matters relating to the Works and will provide the Superintendent with a copy of any incident notification provided to NT WorkSafe under the *WHS Act* at the same time or as soon as practicable after such notification is made to NT WorkSafe.

## Right of Principal to Monitor and Audit

The Principal or its nominee may, at any time, monitor, inspect or audit the performance of the Contractor in relation to its compliance with the WHS Management Plan and this clause 31 generally and the Contractor must allow the Principal or its nominee access to the Site, the  
WHS Management Plan and any relevant documents or activities so as to enable such monitoring, inspection or audit to occur.

## Powers of Superintendent Regarding Work Health and Safety

If the Superintendent considers that there is:

1. a risk of injury to people or damage to property arising from the Works; or
2. an unsafe or potentially unsafe practice or breach of the requirements of this clause 31,

then, in addition to any other rights the Principal has under the Contract, the Superintendent may:

1. direct the Contractor to change its manner of working; or
2. suspend the performance of the Works associated with the unsafe practice or breach, and not lift the suspension until the work area is made safe and the unsafe practice removed, or the breach rectified.

All costs and delay and disruption caused by any action taken under this clause 31.8 are the responsibility of the Contractor.

## Works Involving Asbestos

If the Works include Works Involving Asbestos (as that term is defined in the *WHS Act*) the Contractor must ensure that it, its employees and its sub-contractors comply with all requirements of the *WHS Act* applicable to Works Involving Asbestos.

## Design, Manufacture and Installation Safety Matters

Where the Contract requires the Contractor to design, install or manufacture all or part of the Works, (including management or supervision of a design, installation or manufacture component) the Contractor must ensure that it and its consultants and sub-contractors comply with the *WHS Act* and ensure that any Structure, Plant or Substance it designs, installs or manufactures (or manages the design, installation or manufacture of, as the case may be) is, so far as is reasonably practicable, designed, installed or manufactured without risk to the health and safety of persons who will use, occupy, construct, handle or carry out any activity at or in the vicinity of the Structure, Plant or Substance (as the case may be). In particular, the Contractor must:

1. implement a risk management process to ensure that any hazards associated with the design, installation or manufacture are identified, assessed and, as far as reasonably practicable, eliminated or minimised;
2. consult, cooperate and coordinate with others who may contribute to the safe design, installation or manufacture of the Structure, Plant or Substance including the Principal, sub-contractors and end users;
3. maintain appropriate records regarding the design process and the risk management process, including the results of any calculation, analysis, testing or examination, risk assessment and any conditions to ensure the Structure, Plant or Substance is safe, and provide such records to:
4. the Principal and each person who is provided with the design or Structure, Plant or Substance (as the case may be); and
5. any other person who uses, occupies, constructs, handles or carries out any activity at or in the vicinity of the Structure, Plant or Substance (as the case may be) on request;
6. provide the Principal with any information it requests that is relevant to the design, installation or manufacture of any Plant, Structure or Substance; and
7. on completion of the design, installation or manufacture, provide a report to the Principal detailing the health and safety aspects of the design, Structure, Plant or Substance (as the case may be) which includes information about any identified or potential hazards, hazardous substances used in the design, installation or manufacture, access problems or any handling risks associated with the design, installation or manufacture. Such report will be in a form approved by the Superintendent.

## Breach by Contractor

1. Where, in the reasonable opinion of the Principal or the Superintendent, the Contractor has:
2. where applicable, commenced the Works without having first complied with clause 31.2(b); or
3. committed a breach of any of its other obligations under clauses 31.2 to 31.10, the Principal may immediately terminate this Contract by written notice to the Contractor.
4. The remedy provided in clause 31.11(a):
5. applies notwithstanding any other provision of the Contract; and
6. is in addition to the other remedies under this Contract.

## Work in the vicinity of Power and Water Assets

Prior to commencing work in the vicinity of any sewerage system, high voltage cable or power line or other high voltage structure, the Contractor shall contact Power and Water and obtain and become cognisant with written guidelines or procedures setting out safe practices for working in or adjacent such hazardous areas.

Whilst working in the vicinity of sewerage systems, high voltage cables or power lines or other high voltage structures the Contractor shall follow all directions and instructions issued by Power and Water.

## Work in the vicinity of Natural Gas Pipelines

In accordance with the *Energy Pipelines Act*, the Contractor shall obtain the written approval of the operator of the pipeline before commencing any of the following activities in the vicinity of high-pressure natural gas pipelines:

1. Any activities within the pipeline right-of-way, which involve construction of any kind including:
2. excavation for drains, pipelines or sewers;
3. excavation for buried utilities or services;
4. construction or maintenance of roads or tracks;
5. boring of holes for fence posts or installation of power/telephone poles;
6. any survey or exploration work involving excavation, explosives or vibration.
7. Any nearby construction activities that is likely to affect the right-of-way, such as re-routing surface water flows, construction of high voltage lines, or erection of large metal structures.
8. Any passage of heavy vehicles and equipment over the pipeline other than on public roads.

Whilst working in the vicinity of natural gas pipelines the Contractor shall follow all directions and instructions issued by the operator of the pipeline.

## Fire Precautions

The Contractor shall take all necessary precautions to ensure that no fire hazard is created through the carrying out of the Works.

Where a fire alarm is activated due to actions of the Contractor or his Sub-Contractors, resulting in a call out of the Fire Service, the Contractor will be required to pay for the subsequent call out fee.

## Scaffolding and Excavation

All scaffolding and excavation must conform to the *Work Health and Safety (National Uniform Legislation) Act 2011 (NT)*. The Contractor is to provide all ladders and scaffolding necessary to carry out the Works.

## Disabled Access

Where there is likelihood that the Works may cause a danger or inconvenience to the disabled, the Contractor shall seek advice from the Department of Health, Office of Disability. The Contractor may be required to advertise in relevant newspapers or on community radio programs giving forewarning of the Works.

# Precautions in Carrying Out Works

The Contractor and sub-contractors shall comply with all requirements under Acts, orders and rules and other special requirements of proper Authorities concerning storage, transport and use of materials, plant, equipment; work processes and safety precautions.

The Contractor and sub-contractors shall observe all rules and regulations in force in the area where the Works are to be carried out.

Where any current Australian standard published by Standards Australia is appropriate to storage, transport and use of materials, plant, and equipment, to work processes or to safety precautions, the provisions of such standard shall be observed except if it conflicts with any statutory or special requirements of proper Authority in which case the latter shall apply.

In the absence of any such statutory or special requirements or relevant Australian Standard, the Contractor and all sub-contractors shall ensure that suitable procedures are observed and all proper care is taken.

# Damage to Services

The Contractor shall contact the officer-in-charge of the area that includes the work Site, or his representative, before work commences and in company with the Superintendent check with them the location of all services.

The Contractor shall immediately notify the Superintendent and the officer-in-charge of the area, in the event of damage to any water, gas, steam, compressed air, electric, drainage, sewerage, telephone, fire alarm, control cable or other services in the area.

The Contractor shall render any assistance required in connection with any such incident, but otherwise work in that vicinity shall be stopped immediately and not recommenced until instructions are received from the Superintendent.

Where the service is indicated on the drawing and/or in the Scope of Works, or is evident on the Site, or has been pointed out by the officer-in-charge of the area or by the Superintendent or by a representative of either, the Contractor shall be liable for the cost of any necessary repairs.

Where the Contractor encounters any services, details of which are not given in the drawings and/or Scope of Work and which are not evident on the site or which have not been pointed out to him, and has carried out his operation with reasonable care, the cost of reinstatement, diversion or other associated work may be paid as an extra to the Contract.

# Care of Work and Cleaning Up

The Contractor shall keep the Site clean and tidy as they proceed and regularly remove from the Site rubbish and surplus material arising from the execution of the Works. On Completion of the Works the Contractor shall clear away and remove from the Site all constructional plant, surplus materials, rubbish and temporary works of every kind and shall leave the site of the Works, existing structures and areas adjacent thereto in as good a state of repair as they were in when he commenced the Works excluding for fair wear and tear.

# Protection and Provision for Traffic

The Contractor shall provide all necessary lights, barriers, flags and the like to ensure the safety of all persons, vehicles and animals.

# Protection for Occupants

Where work is carried out in occupied or partially occupied premises the Contractor shall arrange the execution of the Works to minimise nuisance to the occupants. The occupants are to be protected against fumes, dust, dirt, noise or other nuisance.

# Protection of Property

The Contractor shall take all necessary precautionary measures to protect all property against loss, theft or damage resulting from the activities of the Contractor, sub-contractors and agents.

# Protection of Equipment

All equipment, whether supplied under the Contract or existing at the site and surroundings, likely to be damaged or affected by ingress or deposit of foreign matter resulting from the Contractor's operations or those of sub-contractors or agents shall be properly protected by the Contractor. If necessary protected equipment shall be able to function.

# Strong Wind Precautions

The Contractor shall ensure that unfinished work, equipment, sheds, hoardings, materials and any other movable items on the site, are protected, stored, or secured to the extent necessary to ensure that in strong wind conditions they will not be a danger to persons or property because of collapse, movement or any other cause.

# Custody of Keys – Power and Water Assets

Where applicable, the Contractor will be provided with keys for the purposes of accessing Power and Water assets.

The Contractor must not label the keys with the name of the asset or make duplicate keys and shall take all care to prevent theft or loss of the keys.

All keys issued to the Contractor shall be returned at the Completion of the Contract. Failure to return keys within seven (7) days of Contract Completion occurring will incur a fee of $100.00 per key.

The cost of replacing lost or stolen keys shall be at the Contractor’s expense and if the Superintendent so determines shall include the cost of replacing or re-keying master locks.

# Variations

The Superintendent may direct a variation to the Works and such direction shall not invalidate the Contract. The variation shall be valued by mutual agreement between the Contractor and the Superintendent or failing agreement by the Superintendent and the Contract price or rate increased or decreased accordingly.

# Defects Liability Period

Upon determination by the Superintendent that the Works have been satisfactorily completed, the Defects Liability Period, if any, shall commence. The Contractor shall maintain the Works for the Defects Liability Period stated in the Annexure and shall make good at his own expense all defective workmanship or materials and all damage, loss or injury to the Works occasioned by faulty workmanship or materials. If the Contractor fails to make good any defects within a reasonable time or within the time stipulated in a direction given by the Superintendent, the Superintendent may, by notice in writing, take action to complete those defects outstanding at the Contractor's expense.

# Assignment

The Contractor shall not assign the Contract, mortgage, charge or encumber any of the monies payable under the Contract or any other benefit whatsoever arising under the Contract without written consent of the Principal. Such consent shall not be unreasonably withheld.

# Sub-Contracting

Should the Contractor desire to sub-contract any part or parts of the Works he shall submit to the Superintendent the names of his proposed sub-contractors the nature and value of the work, which it is intended they undertake, their CAL Registration Number (if applicable) and seek the written approval of the Superintendent in respect of them. No sub-contractor shall be employed in connection with the Works unless such approval is first obtained. Such approval shall not be unreasonably withheld.

If Contractor Accreditation is applicable to work to be sub-contracted under the Contract the Contractor shall ensure that all sub-contractors and their sub-contractors for any part of the Works valued at over $50,000 are accredited by Contractor Accreditation Limited to an appropriate category/group/sub-group and rating.

Any sub‑contract shall be in writing and contain the provision that progress payments to the sub-contractor shall be made within fourteen (14) days after the Contractor has received payment from the Principal.

Any approval by the Principal to engage a sub-contractor for any part of the Works shall not relieve the Contractor from any of its liabilities under the Contract. The Contractor shall be fully liable to the Principal for the work of the sub-contractor or any employee or agent of the sub-contractor.

# Disputes

Each party must follow the procedures in this clause 45 before starting court proceedings, other than for interlocutory relief.

Any party to this Contract who wishes to claim that a dispute has arisen must give written notice to the other party setting out details of the dispute.

Within five (5) Business Days of the provision of the written notice, a nominated representative of each of the parties must meet to take whatever actions or investigations as each deems appropriate, in order to seek to resolve the dispute.

If the dispute is not resolved within five (5) Business Days of the parties meeting (or within such further period as the parties agree is appropriate) then one or both parties may nominate a mediator to determine the dispute.

If the parties fail to agree to the identity of a mediator within five (5) Business Days of a party nominating a mediator, then either or both of the parties may refer the matter to the President for the time being of the Law Society of the Northern Territory who will nominate a mediator to mediate the dispute.

The parties will bear the costs of the mediator equally.

During disputes and until such time that work under the Contract are completed, the Contractor must, at all times, continue to fulfil its obligations under the Contract and comply with all directions given to it by the Principal in accordance with the provision of the Contract, provided that such directions do not touch upon the subject matter of the dispute in respect of which written notice has been given in accordance with this clause.

# Termination

If the Contractor fails to carry on the Works at a rate of progress satisfactory to the Superintendent, or neglects or omits to carry out any instruction of the Superintendent in respect of the Works or fails to complete the whole of the Works within the period specified for completion or such extended time as the Superintendent may approve, or intimates that he is unwilling or unable to complete the Works, or becomes insolvent or bankrupt, or being a company goes into liquidation, the Superintendent may, by notice in writing either:

1. terminate the Contract whereupon all sums of money which may remain in the hands of the Principal together with all materials on or about the site which are the property of the Contractor and have been provided by him for the purpose of carrying out the Works may be forfeited to the Principal and on being so forfeited shall become vested in or become payable to the Principal; or
2. take the Works wholly or partly out of the control of the Contractor, or any other person in whose control or possession the Works or part of them may be, and complete the same by any other means he so decides. The Principal may take possession of and permit other persons to use any materials, plant or other things on or about the site of the Works, which are the property of the Contractor and are deemed to be requisite and necessary for the purpose of any such completion.

# Rights of Principal to Recover Monies

Without limiting the Principal's rights under any other provision in the Contract should the Superintendent take action pursuant to Clause titled “Defect Liability Period” and/or “Termination” sub-clause (b) or any other clause in this Contract then all losses, costs, charges, outgoings and expenses incurred or sustained by the Principal in completing the Works or rectifying any breach of the Contractor under this Contract will be deemed to be a liquidated debt due to the Principal by the Contractor and will be deducted and set off from any monies that may then or may thereafter become due to the Contractor whether under this Contract or any other Contract whatsoever between the Principal and the Contractor and if the monies are less than the amounts so deductible then the amount of the deficiency shall be a liquidated debt due by the Contractor to the Principal.

Without prejudice to any other rights available to the Principal to recover such a liquidated debt the Principal may demand payment for and recover such liquidated debt against any bank guarantee, guarantee or other security that the Contractor may have given to or in favour of the Principal pursuant to this Contract or any other Contract whatsoever between the Contractor and the Principal.

# Contractor's Performance Report

The Contractor agrees that upon Completion or the termination of the Contract:

1. the Superintendent will prepare a Contractor's Performance Report (’**Report**’);
2. the Superintendent shall liaise with the Contractor in completing the Report although the Superintendent reserves the ultimate right to complete the Report (other than the contractor's comments); and
3. the Principal will use and/or release the Report to Contractor Accreditation Limited and be entitled to release the report to any other department of the Commonwealth or any State or Territory for assessment for future work.

The Contractor agrees that neither the Contractor nor any other person shall have any claim against the Principal or employees or agents of the Principal under any circumstances as a result of the preparation and use of the Report.

# Goods and Services Tax

For the purposes of this Clause unless the context otherwise requires:

**'GST'** means any tax imposed on Supply by or through the *New Tax System (Goods and Services Tax) Act 1999* (‘**Act**’) and any related *Tax Imposition Act* and "New Tax System Changes" has the meaning it bears in the *New Tax System (Trade Practices Amendment) Act 1999* (‘**TPA**’). Where any other term is used in this clause which is defined in the Act or the TPA it shall have the meaning which it bears in the Act, or (if the term is not defined in the Act) then the meaning which it bears in the TPA;

**'GST Rate'** means the percentage amount of GST payable determined under section 9-70 of the Act as amended from time to time;

**'Input Tax Credit'** has the meaning it bears in the Act;

**'Recipient' 'Entity' and 'Supplies'** have the meaning they bear in the Act, and, in addition for the purposes of this contract shall also be read as follows:

1. "**Entity**” shall also mean Contractor;
2. “**Recipien**t” shall also mean Principal;
3. “**Supplies**” shall also mean the Works.

**'Adjustment'** means each form of adjustment to consideration provided for in this clause.

The parties acknowledge that the consideration under this Contract is inclusive of GST, where GST is calculated using the GST rate at the time of forming this Contract.

The Contractor shall provide the Recipient with a Tax Invoice and/or adjustment notes in relation to the supply prior to an amount being paid by the Recipient under this Contract, and shall do all things reasonably necessary to assist the Recipient to enable it to claim and obtain any Input Tax Credit available to it in respect of a Supply.

Where the GST rate is changed after the date of formation of this Contract the consideration under this Contract will be increased or decreased so that the consideration remains inclusive of GST, with GST calculated using the new GST Rate from the date of the change of the GST Rate that applies at the date of formation of this Contract.

# Privacy

For the purposes of this Clause unless the context otherwise requires:

**'Act'** means the *Information Act (NT)*;

**'Privacy Laws'** means the Act; and the Information Privacy Principles set out in the Act or any "code of practice" approved under the Act that applies to any of the parties to this Contract.

**'Personal Information'** means all information about a person that is “personal information” as defined in the Act, which is collected and/or handled by any of the parties in connection with this Contract.

The Contractor agrees to deal with all Personal Information in a manner, which is consistent with the Privacy Laws and any other relevant privacy legislation, as if the Contractor were a public sector organisation.

The Contractor is to collect, use, disclose or otherwise deal with Personal Information only for the purposes of fulfilling its obligations under this Contract.

The Contractor is not to disclose Personal Information without the written authority of the Principal, and in any event disclosure is to be in accordance with the Privacy Laws. The Contractor is to immediately notify the Principal where it becomes aware that a disclosure of Personal Information may be required by law.

The Contractor is to ensure that any employees, agents or sub-contractors, and any other person who may have access to Personal Information held by the Contractor, are aware of the obligations of the Contractor under this Contract and undertake to not collect, access, use, disclose or otherwise deal with Personal Information except in performing their duties of employment and in accordance with this Contract.

The Contractor is to take all reasonable measures to ensure that Personal Information is protected from misuse, loss, unauthorised access, modification, disclosure or other misuse and that only personnel necessary to fulfil the obligations under this Contract have access to the Personal Information.

The Contractor is to develop, and obtain the written approval of the Principal:

1. policies for the management of personal information; and
2. complaint handling procedures.

Each party is to immediately notify the other when a complaint is received. The Contractor acknowledges that individuals have the right to request access to, or correction of, the Personal Information held about them.

The Contractor must not transfer Personal Information outside the Northern Territory without the prior approval of the Principal. The Contractor, in respect to Personal Information, is to immediately notify the Principal where the Contractor becomes aware of a breach of this clause or the Privacy Laws. When this Contract expires or is terminated, the Contractor must, at the Principal's discretion either:

1. return to the Principal all records containing Personal information; or
2. retain any material containing Personal Information in a secure manner as approved by the Principal; or
3. destroy or delete any Personal Information.

This sub-clause will survive the expiration or termination of this Contract.